## Tabelle1
WP n° | Deliverable n° | Title | Version | Lead beneficiary | Person month | Nature | Dessimination level | Document type | Delivery date from Annex I | Forecast date | Status
1 | 1 | Minutes of kick-off meeting | 1.0 | UGOE | 1.0 | Report | RE | pdf | 31.08.2012 (month 2) | 31.08.2012 | Accepted
1 | 2 | Report of meeting in month 6 | 1.0 | UGOE | 1.0 | Report | PP | pdf | 31.12.2012 (month 6) | 31.12.2012 | Accepted
1 | 3 | Report of meeting in month 12 | 1.0 | UGOE | 1.0 | Report | PP | pdf | 30.06.2013 (month 12) | 30.06.2013 | Accepted
1 | 4 | Report of meeting in month 18 | 1.0 | UGOE | 1.0 | Report | PP | pdf | 31.12.2013 (month 18) | 31.12.2013 | Accepted
1 | 5 | Report of meeting in month 24 | 0.0 | UGOE | 1.0 | Report | PP |  | 30.06.2014 (month 24) | 30.06.2014 | Submitted
1 | 6 | Report of meeting in month 30 | 0.0 | UGOE | 1.0 | Report | PP |  | 31.12.2014 (month 30) | 31.12.2014 | Pending
1 | 7 | International Symposium | 0.0 | UGOE | 10.0 | Other | PU |  | 31.05.2015 (month 35) | 31.05.2015 | Pending
2 | 1 | Identification of candidate semiochemicals that repel or confuse target pests | 1.0 | FHB | 105.0 | Report | RE | pdf | 30.06.2013 (month 12) | 30.06.2013 | Accepted
2 | 2 | Results of the screen for polymers, additives and minimum doses of activ ingredients with EEAs | 1.0 | FHB | 67.0 | Report | RE | pdf | 30.06.2013 (month 12) | 30.06.2013 | Accepted
2 | 3 | Report describing the development of co-fomulated products based on EPF and EEAs | 0.0 | FHB | 30.0 | Report | PU |  | 30.06.2014 (month 24) | 30.06.2014 | Pending
2 | 4 | Report describing the capsules containing EPF | 0.0 | FHB | 42.0 | Report | RE |  | 30.06.2014 (month 24) | 30.06.2014 | Pending
2 | 5 | Report describing novel capsules and co-formulation of EPF with efficiacy enhancing agents | 0.0 | FHB | 34.0 | Report | PU |  | 30.06.2015 (month 36) | 30.06.2015 | Pending
2 | 6 | Report on upscaling of EPFs and EPNs | 0.0 | ENE | 11.0 | Report | PU |  | 30.06.2015 (month 36) | 30.06.2015 | Pending
3 | 1 | Defined technical protocol for test of side effects on invertebrates established | 2.0 | UCPH | 11.0 | Report | PU | pdf | 31.08.2013 (month 14) | 31.08.2013 | Accepted
3 | 2 | Cohort-rearing of invertebrate non-target BCAs for side-effect testing established | 1.0 | UCPH | 12.0 | Other | RE | pdf | 31.10.2013 (month 16) | 31.10.2013 | Accepted
3 | 3 | Molecular tools for identification of EPFs | 1.0 | UCPH | 14 | Report | PP | pdf | 31.12.2013 (month 18) | 31.12.2013 | Accepted
3 | 4 | Refinement of RAFBCA protocols | 0.0 | UCPH | 47.0 | Report | PU |  | 30.06.2015 (month 36) | 30.06.2015 | Pending
3 | 5 | Determination of the cytotoxity and geneotoxicity | 0.0 | UCPH | 14.0 | Report | PU |  | 30.06.2015 (month 36) | 30.06.2015 | Pending
3 | 6 | Report on risk assessment | 0.0 | UCPH | 16.0 | Report | PU |  | 30.06.2015 (month 36) | 30.06.2015 | Pending
3 | 7 | Manuscript on effects of fungal BCA - EEA combinations | 0.0 | UCPH | 28.0 | Report | PU |  | 30.06.2015 (month 36) | 30.06.2015 | Pending
3 | 8 | Report on direct and indirect effects of fungal BCA - EEA combinations | 0.0 | UCPH | 37.0 | Report | PU |  | 30.06.2015 (month 36) | 30.06.2015 | Pending
3 | 9 | Manuscript on effects of fungal BCA - EEA combinations on non-target invertebrates | 0.0 | UCPH | 9.0 | Report | PU |  | 30.06.2015 (month 36) | 30.06.2015 | Pending
4 | 1 | Report on the efficacy of the commercially viable EPF strains | 2.0 | SU | 14.0 | Report | CO | pdf | 30.09.2013 (month 15) | 30.09.2013 | Accepted
4 | 2 | Report on the efficacy of the lure and kill strategy against wireworms | 3.0 | SU | 12.0 | Report | CO | pdf | 30.09.2013 (month 15) | 30.09.2013 | Accepted
4 | 3 | Report on the efficacy of the lure and kill strategy under semi-field conditions | 2.0 | SU | 10.0 | Report | PU | pdf | 31.12.2013 (month 18) | 31.12.2013 | Accepted
4 | 4 | Report on the synergistic effects | 0.0 | SU | 30.0 | Report | PU |  | 30.04.2015 (month 34) | 30.04.2015 | Pending
4 | 5 | Report on the efficacy of the lure and kill strategy under field conditions | 0.0 | SU | 16.0 | Report | PU |  | 30.04.2015 (month 34) | 30.04.2015 | Pending
4 | 6 | Recommondations on using lure and kill strategies | 0.0 | SU | 13.0 | Report | PU |  | 30.04.2015 (month 34) | 30.04.2015 | Pending
4 | 7 | Report on the efficacy of semiochemical repellents | 0.0 | SU | 15.0 | Report | PU |  | 31.05.2015 (month 35) | 31.05.2015 | Pending
4 | 8 | Report on the efficacy of novel formulations | 0.0 | SU | 20.0 | Report | PU |  | 30.06.2015 (month 36) | 30.06.2015 | Pending
4 | 9 | Report on the most cost effective, synergisstic formulated products | 0.0 | SU | 18.0 | Report | PU |  | 30.06.2015 (month 36) | 30.06.2015 | Pending
5 | 1 | Comparative economic assessment of biological control products at producer level | 1.0 | TUM | 14.0 | Report | PP | pdf | 31.10.2013 (months 16) | 31.10.2013 | Accepted
5 | 2 | Cost assessment of relevant ecotoxological testing requirements | 0.0 | TUM | 10.0 | Report | PU |  | 30.06.2014 (months 24) | 30.06.2014 | Pending
5 | 3 | Business plans | 0.0 | TUM | 11.0 | Report | RE |  | 30.06.2015 (months 36) | 30.06.2015 | Pending
5 | 4 | Expected wellfare benefits and costs of BCAs at EU level | 0.0 | TUM | 14.0 | Report | PU |  | 30.06.2015 (months 36) | 30.06.2015 | Pending
5 | 5 | BCA software program | 0.0 | TX | 41.0 | Report | PU |  | 30.04.2015 (month 34) | 30.04.2015 | Pending
6 | 1 | Project Fact Sheet | 2.0 | ENE | 2.0 | Other | PU | pdf | 31.07.2012 (month 1) | 31.07.2012 | Accepted
6 | 2 | Construction of website | 1.0 | UGOE | 4.0 | Other | PU | Typo3 | 31.08.2012 (month 2) | 31.08.2012 | Accepted
6 | 3 | Dissemination of project knowledge incl. IPR | 0.0 | ENE | 12.0 | Report | RE |  | 30.06.2015 (month 36) | 30.06.2015 | Pending
6 | 4 | Policy brief fact sheet | 0.0 | ENE | 3.0 | Report | PU |  | 30.06.2015 (month 36) | 30.06.2015 | Pending